Progress Report - PMNCH 2020

Rolling Workplan for 2020 of deliverables funded by PMNCH and/ or directly facilitated by PMNCH Secretariat

Status key at 6 months (30 May 2020) and at 1 year (31 December 2020)

|  | Deliverable is completed |
| --- | --- |
|  | Started and is currently on track and will be completed by 31 December 2020 |
|  | In process but at risk - risks identified that may cause delay, budget overrun and / or alteration of plans |
|  | Work has stopped and will not be delivered to plan and budget, due to, for example, lack of funds, change in priorities, other partners doing this work, etc. |

| Cross thematic deliverables | Priority Deliverables in 2020 |  | Status |  | Additional details/comments |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 6m | 1yr |  |  |  |
| ANALYSIS |  |  |  |  |  |  |  |
| Partners: Access & use of knowledge to enhance policy, service delivery and financing mechanisms for WCAH |  |  |  |  |  |  |  |
| Secretariat: Facilitate consensus building, and knowledge synthesis development & dissemination, including digital content |  |  |  |  |  |  |  |
| Knowledge synthesis for global and country-led advocacy: - BMJ series on equity: "Leaving no woman, child, and no adolescent behind " developed with Countdown 2030, UNICEF and WHO. Five-year progress report on WCAH. https://www.bmj.com/leaving-no-one-behind and including comments by Helen Clark and Dr Tedros. Launched at the PMAC, Bangkok in January 2020 to stimulate discussion and exchange among policy makers, funders and NGOs. https://www.who.int/pmnch/media/news/2019/health_for_all_by_2030/en/ |  |  |  |  | Completed in January 2020. Planning a podcast for the 1-year mark which will include an interview with Helen Clark |  |
| - Covid-19 repository of resources/toolkits on WCAH. Living digital compendium of up to-date guidance and partners’ resources, aligned with official WHO recommendations. https://www.who.int/pmnch/media/news/2020/guidance-on-COVID-19/en/ The WCAH and COVID19 toolkits are also showcasig advocacy & communications materials as well as country lessons and field experiences, with a view of providing multi-media information packages that are action-oriented and user-friendly. Will be released on a rolling basis starting in June 2020. |  |  |  |  | The COVID-19 and WCAH Compendium is updated on an ongoing basis with the latest WHO and UN guidance. The first set of digital toolkits (MNH, Child Development and Adolescent Health) was launched on 10/11 December at the PMNCH Lives in the Balance 2 Summit. |  |
| - Global Investment Framework on WCAH including preparedness and response Systematic review incl. strategies & interventions to mitigate the health and socio-economic impacts of epidemics and pandemics on WCA ). Second phase will include economic analysis and costing of SRMNCAH and multi-sectoral interventions for all LMICs, as well as social-economic returns on investments, with a view of developing key advocacy asks on policy and financing. |  |  |  |  | Concept Note developed on the Global Investment Framework and agreement to co-develop Framework with GFF, World Bank and WHO. Systematic review protocol finalised and to be published in 2021. |  |
| - Cost-effective analysis of public financing of package of RMNCH interventions and financial-risk protection to inform advocacy messages. Peer-reviewed articles include: 1) Extended cost effectiveness analysis of public financing of a package of RMNCH interventions to children living in families at different wealth/income status in Nigeria. Duke University in the lead. 2) Economic analysis on Social, Behavioural and community engagement (SBCE) interventions for RMNCH: analysis of the impact of scaling-up SBCE interventions for immunization, antenatal care (ANC), skilled birth assistance (SBA) at childbirth and postnatal care (PNC), focusing on three important groups of SBCE interventions including inter-personal communication, community mobilization, and mass media. |  |  |  |  | Extended cost effectiveness analysis of RMNCH interventions in Nigeria completed and draft article developed; SBCE analysis completed for immunization services; Scope of Work developed for ANC, SBA and PNC – contract developed with Duke University |  |
| Partner capacity building - IPU Handbook on roadmap for WCAH action developed: Https://www.ipu.org/resources/publications/handbooks/2020-02/road-map-action-womens-childrens-and-adolescents-health, Analysis of facilitating factors for parliamentarian action for WCAH published, and capacity building webinars held for parliamentary staff |  |  |  |  | Completed and widely distributed to all parliaments |  |
| - Peer-reviewed article to promote multi-sectoral strategies for WCAH, incl. COVID-19 response across sectors: https://drive.google.com/open?id=1STcdiznhf8bk6DfTm0iELZ9xMwrArSs8 |  |  |  |  | Completed and widely distributed with over 100,000 reached |  |
| ALIGNMENT |  |  |  |  |  |
| Partners: Align to increase WCAH commitments and financing and integrate incl. GFF Investment Cases (GFF ICs), through strengthening multi-stakeholder, multisectoral platforms at country level |  |  |  |  |  |
| Secretariat: Support partners and constituency engagement, alignment and consensus building |  |  |  |  |  |
| Support PMNCH constituencies to ensure engagement in national plans (including GFF ICs) - Continue support to 14 national multi-stakeholder platforms through WHO/H6 to engage constituencies to focus on WCAH priorities, joint advocacy and accountability. Due to COVID-19, H6, and implementing partners have requested an extension until 2021: https://drive.google.com/file/d/1m_rLFIwFVw52IgUTtrjFFHVWMvqve0JZ/view?usp=sharing . All countries' plans are available here https://drive.google.com/drive/folders/1g2rsLgU34q51HiKtuVmDEZPXyppsXXyo?usp=sharing |  |  |  |  | 13 MSPs are in different stages of operationalisation as implementation was delayed due to COVID-19. The workplans for MSPs have been adapted as part of countries’ COVID response focusing on WCAH. Funding for PMNCH supported MSP through the H6 mechanism will not go forward in 2021 instead modalities suggested in the country engagement paper endorsed by the Board in 2020 will be explored and implemented. |  |
| - Support Civil Society Organisation engagement, advocacy and accountability for improved WCAH in the context of COVID-19. Small grants issued to civil society in nine countries in August 2019, with implementation in 2020. Additional grants to be issued in 2020 with a focus on COVID-19 https://www.who.int/pmnch/media/news/2019/small_grants_announced/en/ . |  |  |  |  | Implementation of 2019 grants completed in Q4 2020. Progress report available on demand. Funds received from GFF secretariat in Q4 2020. MSH was contracted in April 2021 and the call for proposals has been issued and closes on 11 June 2021. Grant selection will ensue. Links have been drawn between the grants and the COVID-19 Call to Action as well as the Joint Learning Initiative supported by the GFF, Gavi, GFATM, UHC2030 and PMNCH. |  |
| - Support CSO and youth engagement in GFF processes globally and in countries by hosting and supporting the civil society coordination group, which brings together ~350 CSO reps (including youth) in a space to exchange information and align efforts around engagement in GFF processes and advocacy and accountability for WCAH. Deliverables incl.: supporting youth and CS representatives on the GFF Investors Group, CS consultations around IG meetings through 8 webinars, 4 quarterly newsletters, 4 information sharing webinars on key issues, and regular communication through the google group, support to working groups and partners to implement agreed activities and advocacy. |  |  |  |  | CSO group supported, has held multiple webinars including one replacing the annual workshop which brought together over 120 representatives. Newsletters produced, regular information exchanged. PMNCH also commissioned an analysis of the state of civil society and youth WCAH coalitions and their engagement in planning, the preliminary results have been vetted during the annual workshop and will be published soon. Also supported consultations for the GFF strategy refresh and civil society engagement framework |  |
| - Support regional advocacy and coordination for WCAH through collaboration with HHA, the AU and EWEC LAC. |  |  |  |  | For EWEC LAC, work is on track. Progress report is attached. However, the partner has asked for extension in Q2 of 2021 to finalise documents/tools and the translation. The progress report can be found here. PMNCH through its partner living goods has successfully advocated for the Africa CDC and AU COVID strategy to include language on continuity of essential services. PMNCH also supported Africa CD, the AU and other partners in producing a series of key messages and supports on COVID myth. These have widely been disseminated by partners through TV and other channels. HHA call to action includes the need for advocacy for continued essential services as a key priority |  |
| - GHI: PMNCH and UHC2030 to co-chair and support a task team on funding support for CS engagement, advocacy and accountability |  |  |  |  | Given COVID-19 and the rise of various health alignment processes including the GAP this activity was deprioritized |  |
| Strengthen partner and constituency engagement, incl. digitalizing PMNCH's operations - Digitalization of membership database being finalized and constituency-partner mapping ongoing to feed into constituency engagement strategies. The mapping includes: listing all members and categorizing them by constituency and region , as well as contact details and communication platforms, such as Twitter, Facebook, e-mail addresses, telephone, etc. |  |  |  |  | Soft launch of platform in December 2020 |  |
| - Update and revamp PMNCH membership materials and processes, including implementing electronic application; guidance documents and webinars; welcoming package to new members, etc. Also, revising the Constituencies Management Guidelines to strengthen membership engagement and delivering on PMNCH's partnership-centric approach and will be finalized after the approval of the PMNCH 2021-2025 Strategy. |  |  |  |  | Soft launch of digital action plan in December 2020 |  |
| - Strategy 2021-25 development and consultations – Consultations have been ongoing since Nov.2019 under the leadership of the Strategy Committee. A strategy retreat took place in Feb 2020, which led to the development of an Outline document which has been widely distributed for consultation, including: two webinars; TC with all constituencies and a member survey: https://www.who.int/pmnch/activities/advocacy/globalstrategy/2021_2025_strategy/en/ Phase 1 and Phase 2 have been successfully completed The Strategy 2021-2025 is finalized and it has been circulated widely. It is available at the following link: https://www.who.int/pmnch/about/strategy/2021-2025-strategy/en/ It was launched during the Accountability Breakfast 2020 with the accompanying video. It will be made available also in French, Spanish and Arabic. |  |  |  |  | Completed |  |
| - PMNCH Digital Strategy is finalized with key findings and 67 recommendations. A management document has been developed with updates on the operationalization of the strategy: https://worldhealthorg.sharepoint.com/:x:/r/sites/PMNCHCollaboration/Other%20Documents/Digital%20Strategy%20Recommendations%20(From%20report)1.xlsx?d=w1fafb094b09b4aabaffc86342196c672&csf=1&web=1&e=GXhfGw |  |  |  |  | Has developed into the Digital Action Plan, launched in December and continue to be implemented in 2021. |  |
| Enhance governance procedures and mechanisms - Conduct 2 virtual Board Meetings, one on the 30th of June to review the updated PMNCH 2021-2025 Strategy and another to replace the Board Meeting in Mexico virtual meeting on 14-15 December 2020. |  |  |  |  | Completed |  |
| - Conduct 4 EC meetings (9 April, 9 June, 22 July, 24 Nov.). Organize standing committee (GNC and SC) and constituency meetings (GNC: 14 Feb, 2 and 28 April, 15 May, 2 and 28 April 25 June, 24 July, Gov Reform consultations: 1-16 Oct; 22 Oct, 24 November) and (SC: 16-18 Feb, 5 March, 12 and 14 May, July and 18 Nov). Country Engagement Working Group established and developed country engagement approach which got included in the new Strategy. Accountability WG established and also provided inputs in the new Strategy. Knowledge and Evidence working group and Advocacy WG were also critical in providing inputs to the Strategy. Ad Hoc on Good Governance and Management WG established by the GNC. |  |  |  |  | Completed |  |
| - Support to Board Chair on going, as well as to extended board leadership, standing committees, working groups and each of the ten Constituencies. |  |  |  |  | Board Chair, standing committees and all constituencies were successfully supported. |  |
| - Update the PMNCH Governance Standard operating procedures in line with the new Strategy. This will include updating the Board Manual including drafting and finalizing the necessary TORs of the committees and working groups. |  |  |  |  | On track and ongoing – in parallel with the Governance Reform that is ongoing in 2021 |  |
| PMNCH External Audit and Evaluation - Management report to the WHO-led external audit is finalized and approved. |  |  |  |  | Completed and approved by WHA |  |
| - Appraisal of the External Evaluation (https://www.who.int/pmnch/about/strategy/PEEAR.pdf?ua=1 )was developed by the EERG and approved by EC on 9 April. Board speaking points of the external evaluation (https://www.who.int/pmnch/about/strategy/Speaking_points.pdf?ua=1 ) were also approved by the EC as was the Board Management Report (https://www.who.int/pmnch/about/strategy/Board_response2Evaluation.pdf?ua=1 ). The Management Report will be updated ongoingly. |  |  |  |  | Completed and used to inform the development of the new Strategy 2021-2025 |  |
| - PMNCH provided inputs into the EWEC Management Response to the IAP External Evaluation, as well as EWEC Evaluation. |  |  |  |  | Completed and used to inform new Strategy |  |
| ADVOCACY |  |  |  |  |  |
| Partners: Advocate for better policies, more and better financing, and improved service delivery/quality at global, regional and country levels |  |  |  |  |  |
| Secretariat: Facilitate development of advocacy messages, champions, digital content and media products; organize campaigns and advocacy events |  |  |  |  |  |
| Champion engagement: PMNCH will leverage its current and former chairs to mobilize political support at the regional and national level for increased attention to WCAH needs. PMNCH has developed a political engagement strategy, which has fed into the broader PMNCH advocacy strategy and action plan to impact WCAH outcomes in select geographies with highest burden and hugest needs. PMNCH Board Chair, Rt Hon. Helen Clark, former Prime Minister of New Zealand, and previous PMNCH board chairs have led PMNCH advocacy through events, media statements, and meetings, including in relation to those documented in the events calendar and advocacy roadmap for 2020. Selected examples for 2020 include: Commentaries and op-eds (BMJ Equity series commentary on intimate partner violence, Jan. 2020; Lancet Commission on Child Health, Feb 2020; IPV and equity, May 2020, The Telegraph, UK; COVID-19 and WCAH equity, May 2020, Thomson Reuters, global; WASH and menstrual rights, May 2020, The Guardian, UK; Listening to women’s voices, June 2020, Thomson Reuters; foreword to the EWEC@10 global progress report, Sept 2020. Champions have also raised the profile of WCAH through events, including women leaders and Covid-19 round-table, in May 2020 and related press release; and leadership dialogues at the virtual summit related to Covid-19 and WCAH, July 2020, the Accountability Breakfast, September 2020 and Lives in the Balance 2 virtual summit in mid December 2020. PMNCH has also supported parliamentarians to advocate for and support improved WCAH through: 1) IPU Handbook published and launched through online campaign including an op-ed and social media; 2) Op-ed; 3) Analysis of facilitating factors for parliamentarian action for WCAH published in the BMJ; and 4) Online training for parliamentarian staff on the IPU handbook and rolled out for Sub-Saharan Africa |  |  |  |  | Significant deliverables and activities, see links and comments directly in text. |  |
| Advocacy through civil society: Stillbirth advocacy, working through a grant agreement with the Stillbirth Advocacy Working Group, hosted by the International Stillbirth Association. In 2020, this incl. the development of stillbirth parent group registry, message development, a stillbirth advocacy toolkit, and media outreach pegged to the launch of new global stillbirth estimates (end-2020) |  |  |  |  | Deferred to 2021 because of COVID. |  |
| COVID-19 advocacy 1.COVID-19 related advocacy and communications products compiled, widely disseminated (up to 8 knowledge and communication digital toolkits in relation to MNCH, SRHR, adolescent health, and stillbirths); a weekly series of data-based infographics shared through social media channels, including WHO Twitter (7.7 million followers as May 2020), five self-care and behavioural change animated videos, umbrella messaging framework, op-eds, ‘Adolescent health and well-being in times of COVID’ webinars partnering with WHO (mental health and school closures) and inviting speakers (UNICEF, UNESCO); a Helen Clark-led video and/or podcast series, champion statements and op-eds, and a partner-based meeting for knowledge and solution-sharing, e.g., Core Group-PMNCH Virtual Summit on 22 July) 2.PMNCH will develop key advocacy and policy asks based on emerging findings from in-country partners’ work on documenting the lived experiences of WCA during the COVID-19 pandemic feeding into the PMNCH broader advocacy campaign https://drive.google.com/file/d/1Vg0SYFnjUlHL6bfPwwNTf0xQeX6wckxr/view?usp=sharing. The videos include: Breastfeeding released in May 2020, Adolescent Mental Health video was released during the CORE Group conference on 27-28 January 2021; the responsive caregiving was completed and launched in April 2021. The video on violence against women is expected to be completed and launched during 2021. Op-ed in collaboration with WRA and three countries incl. Mexico, India and Kenya published on what women want. Lived experiences report completed and publishing. Following eSummits held successfully with several thousand participants and views: July 1-2: Lives in the Balance 1 summit, Sept. 29 Accountability Breakfast incl. a strong focus on accountability in a time of COVID. Lives in Balance 2 summit, Dec, 11 to mobilize for commitments and reflect, share, collaborate and act on necessary strategies to building back better. Together these events launched the COVID-19 Call to Action and shared 20.6 billion dollars in commitments made by governments and foundations in support of WCAH. These e-summits have provided space for sharing the latest WCAH and COVID-19 related evidence, for exchanging experiences among partners, and for raising the profile of WCAH. Each of these summits has seen an average of 1700 registrants, social media reach ranging between 1 million and 2.7 million and press releases that have generated stories in outlets that reach over 1bn people worldwide. |  |  |  |  | PMNCH’s COVID-19 work is well underway and on track for 2020. More specifically: 1) the first three digital Toolkits on COVID-19 and WCAH were launched in December 2020 (these focus on the following themes: MNH; Child Health and Development; and Adolescent Well-being); 2) Several Op-eds and videos including (self-care animated video series) are under development, the first of which on breastfeeding in times of COVID reached over 80 million views in 2020. |  |
| ACCOUNTABILITY |  |  |  |  |  |
| Partners: Effective tracking of the Global Strategy goals and of national commitments to WCAH, including partner engagement and accountability at national level |  |  |  |  |  |
| Secretariat: Tracking and reporting on EWEC commitments; synthesized progress on outcomes; supported constituencies to use tools to influence WCAH policy |  |  |  |  |  |
| Tracking of WCAH commitments and progress with partners: - Joint BMJ series on equity "Leaving no woman, child, and no adolescent behind" launched at PMAC in January 2020 and widely disseminated throughout the year. A podcast for the 1-year mark which will include an interview with Helen Clark is currently under planning phase. Efforts have been made to streamline Global Strategy Progress Reporting (GSPR), which has also resulted in the agreement among key partners (including CD2030, EWEC, WHO, UNICEF) to develop a joint deep dive report (e.g., BMJ) every 2-3 years and a light GSPR report in between those years. The GSPR EWEC@10 report was launched at the virtual UNGA Accountability Breakfast, where it presented an important theme and informed the discussions during the event, co-led by UNICEF and WHO. |  |  |  |  | Successfully completed with wide distribution, see link to the series and articles, as well as event program for the launch directly in the text. |  |
| - EWEC Commitments Progress Tracking for both state and non-state commitment makers is being conducted again for the 2020 reporting year with the EWEC Secretariat. The analysis were featured in a technical background report, that fed into the larger Global Strategy Progress Report, which was launched during the Accountability Breakfast at UNGA 2020. |  |  |  |  | The EWEC Commitments and Non-State Commitments Progress Tracking and Analyses have been completed. 2020 EWEC Commitments PowerPoint The technical report by the consultant team was finalized in December 2020. |  |
| Partner capacity building in accountability for change - Facilitate review of data visualization tools to improve WCAH planning and programming at country level, with UNICEF & WHO. Draft TORs developed and reviewed. UNICEF will develop an RfP and PMNCH will consider cost sharing. Findings were presented at the Accountability Breakfast at UNGA 2020. |  |  |  |  | Exercise was completed and the report shared with UNICEF in January 2021. |  |
| - The Muskoka2 paper: "Increased aid for RMNCH: findings from application of the new Muskoka2 method, 2002-2017" was published in March 2020. The work has led to an excel workbook that shows users (donors and researchers) how M2 works and how to use it to calculate RMNCH estimates. User-reference note. This work was discussed in the D&F meeting in May / June for uptake by relevant partners. |  |  |  |  | Completed |  |
| - The manuscript "Social accountability for RMNCAH: a review of reviews" has been developed and published and will be included in our compendium of Accountability resources on PMNCH’s website. |  |  |  |  | Completed |  |
| - Develop and make widely available “Guidance / resource toolkit for strengthening accountability mechanisms for WCAH” to support the multi-stakeholder platforms in countries. The outline and design of the resource toolkit has been revised to be integrated with the one-stop-shop PMNCH Accountability Portal, and ultimately into the overall PMNCH Digital Platform. Due to revised timeline this work is anticipated to be completed in 2021. |  |  |  |  | Ongoing. A consultant team has been identified to conduct the mapping and development of the toolkits. Work has started in Q1 2021, with initial mapping of most applied resources. |  |
| - Capacity building of civil society on public finance management and advocacy for improved domestic resource mobilization and utilization for health Jointly organized a webinar on health financing with OSF, AHBN and the GFF CSCG 100 orgs. Joint programme of work on civil society capacity building for health financing agreed with GFF, UHC2030, GFATM, Gavi etc. first global webinar is planned for Nov 2020. |  |  |  |  |  |  |
| IAP Global Accountability (IAP report) PMNCH hosts and provides funding to the IAP Secretariat to support the IAP’s work. The IAP reports to the EWEC High-Level Steering Group, which is chaired by the UN Secretary-General. In 2020, the IAP issued a landmark report: Caught in the COVID-19 storm: women’s, children’s and adolescents’ health in the context of UHC and the SDGs. The report includes country scorecards on progress and success factors, country case studies and accountability framework and recommendations. The report draws on evidence during the COVID-19 pandemic and implications for women’s, children’s and adolescents’ health and rights. Based on the EOSG’s recommendation, this IAP report was released at an official High-Level Political Forum side event in July 2020. The event was co-hosed by the governments of South Africa, Georgia and Japan and co-organized by EWEC, PMNCH, and UHC2030. High-level dignitaries participated in the event, including his Excellency Mr Cyril Ramaphosa, President of South Africa and Chairperson of AU, Rt. Honourable Helen Clark, PMNCH Board Chair (https://iapewec.org/news/launch-of-the-iap-2020-report-watch-live/). The report achieved global attention through a media reach of 600 million across six regions: https://iapewec.org/news/media-coverage/ Other think pieces prepared by the IAP in 2020 include: - IAP BMJ editorial on health equity in the Countdown, H6, PMNCH Leaving no one behind BMJ Supplement: launched and published, January 2020 - IAP WHO Bulletin editorial on UHC provisions for women, children and adolescents in its Special issue on UHC, January 2020 - IAP Lancet editorial on HPV vaccine access and comprehensive guidelines, February 2020 - IAP op-ed in Devex on the occasion of EWEC@10: Why the SDGs' defining decade must focus on accountability for those left behind, September 2020 - A crisis in accountability for women’s, children’s and adolescents’ health, Comment, The Lancet, July 2020 (authored together with iERG Co-Chair, Richard Horton) - Independent accountability for women, children and adolescents under threat, Correspondence, The Lancet, November 2020 The IAP final report entitled “The Health of Women, Children and Adolescents is at the Heart of Transforming our World: Empowering Accountability.’ was submitted to the UN Secretary-General on 31 March 2021 Other updates are available on the IAP’s website: iapewec.org |  |  |  |  | The 2020 IAP report has been virtually launched mid-July 2020, during the High-level Political Forum and it is available at the following link: https://iapewec.org/reports/annual-reports/iap-2020-report/ The final report is available at: https://iapewec.org/news/final-reflections-bring-the-work-of-the-iap-to-a-close/ |  |

| Early Childhood Development – priority deliverables in 2020 | Status |  | Additional details/comments |
| --- | --- | --- | --- |
|  | 6m | 1y |  |
| ANALYSIS Partners: Develop and disseminate ECD innovation and knowledge briefs (including Nurturing Care Framework)Secretariat: Facilitate consensus building; make available agreed knowledge and innovation products (to be decided) through website, communities of practice and workshops, events |  |  |  |
| Case study (India) on implementation of ECD interventions: what has worked, and lessons learned is under development and slightly delayed due to COVID-19, see concept note and interim report: https://drive.google.com/file/d/1PUQ0Cgw_bNwLfy_VCodcEmJlnAzl9lju/view?usp=sharing. https://drive.google.com/file/d/14LE1yp56eeZH2VKrx7gcc_iKgj7Ursth/view?usp=sharing |  |  | The Case study has been completed and submitted to the BvLF. The study can be found here. |
| 4 evidence briefs on ECD to be completed in 2020. Partnering with UNICEF, WHO, World Bank, ECDAN and others on developing webinars on issues affecting children aged 3 and under, including in relation to the current COVID-19 pandemic. Briefs: Nurturing care for children affected by HIV was completed in June 2020 and disseminated via the Nurturing Care website and eblasts reaching over 3000 people. Nurturing care for children living in humanitarian settings was completed in December 2020 but officially launched on January 13, 2021. WHO and IRC both issued articles (See above link) and PMNCH posted it on the PMNCH website and social media. Dissemination will include a panel presentation at the Global Health Practicioners’ conference (Jan 2021) and a multi-country workshop in the Arab region (June 2021). In addition to web-based dissemination, discussions are underway on how to leverage the humanitarian brief to advance country level actions in the Arab region and West Africa. National or multi-country workshops are being explored for the first half of 2021. The tobacco control brief was not completed in 2020 as it was decided to widen the pool of reviewers before finalizing the brief. This brief, along with the two others (newborns, male engagement) will be completed in 2021. Two more briefs (bringing the total to 5) are under development but will not be completed in 2020. The topics are small and sick newborns and engaging male caregivers in providing nurturing care. The former has been delayed as the writing group decided to engage the support of a new writer to bring the content closer to the desired vision. The latter is a new brief that was added to the set in October 2020. Plan International and Promundo are lead authors. In July 2020, PMNCH together with WHO, UNICEF, ECDAN and the World Bank organized a webinar on ensuring safe breastfeeding during COVID-19. The webinar included speakers from Viet Nam, Colombia and Brazil. The webinar was attended by over 300 participants and the recording has been viewed over 300 times. |  |  | On track with many deliverables in 2020 completed and widely distributed. |
| BMJ paper on "Inequalities in early childhood development" developed and launched at PMAC, January 2020 |  |  | Completed and widely distributed. |
| ALIGNMENT Partners: Promote adoption of NCF by 192 countries (WHA 2018) & its principles in 5 countries (2019-2020) Secretariat: Organize meetings and align partners behind ECD/NCF; support work in 5 countries |  |  |  |
| Organize with WHO, UNICEF, World Bank Group, ECDAN and AfECN two national multi-stakeholder and multi-sectoral workshops to further attention to and investment in ECD in the health sector and beyond. (https://drive.google.com/file/d/1xYxQMC0QtC4EH-7WIb8qdrz2DnWBgL-V/view?usp=sharing ) Burundi and Madagascar will organize a range of activities in November and December to advance attention to and investment in ECD in the two countries. Burundi is building on the work that took place in July 2019 to update and validate the national nurturing care for ECD action plan as well as advance finalisation of a national strategy for nutrition focusing on children 4 years and younger. Madagascar is holding a high level meeting with the Prime Minister, 5 Ministers, and heads of agencies. This will conclude with participants signing a declaration of their commitment to investing in ECD. This will be followed by a 3 day technical meeting which will include finalizing the national multisectoral ECD strategy. There will also be a training for 35 journalists with the aim of involving the media more in covering and advocating for ECD. |  |  | On going with following deliverables either completed or taken forward to 2021: Madagascar – completed (December 2020). Burundi – postponed to February 2021 to allow for participation of the First Lady in a national 2-day workshop. |
| Contributing to the work of the ECD / NCF coordinating team, including the activation of the working groups - PMNCH chairs the bi-weekly meetings ensuring information sharing, ongoing collaboration across the five partners (WB, UNICEF, WHO, ECDAN, PMNCH) as it pertains to individual and collective actions that can generate greater visibility for work happening regarding nurturing care at global, regional, and national levels. |  |  | Completed |
| ADVOCACY Partners: Develop and integrate advocacy messages and products on NCF/ECD into advocacy campaigns in 5-10 countries Secretariat: Produce and disseminate advocacy products and digital content; co-organize NCF and ECD advocacy campaigns and events |  |  |  |
| Continue to manage and update the nurturing care website and Twitter account, weaving in COVID-implications. A COVID-19 page was added to the nurturing care site providing quick access to partners’ websites and key resources. The website has, on average, 1500 visitors per month. In the months when we have an eblast we have about 2200 visitors. We’ve had a five-fold increase in Twitter followers since Jan 2020 (currently over 600). Anecdotal feedback indicates that users are pleasantly surprised by how much information is now readily available on the site. It is increasingly becoming the one-stop show that was envisioned when the site was created. |  |  | Knowledge updates completed and impressive increase in reach achieved in 2020 |
| Coordinated the development of a digital and advocacy toolkit for ECD in Health with partners in the NC for ECD Advocacy Working Group (https://drive.google.com/file/d/1ASEbPnP0rrWpEFil8U-z0WbXncK1fGa_/view?usp=sharing ) Developed by the PMNCH Nurturing Care for ECD Advocacy Working Group, the Toolkit provides a repository of practical tools and resources for anyone wishing to advocate for increased attention to and investment in ECD with and through the health sector. The digital and living Toolkit includes key messages, country experiences, country profiles, details on what is meant by nurturing care and FAQs, advocacy ‘how to’, thematic briefs, quotes from champions and a relevant resources composite. The Toolkit will continue to be updated as new materials are identified or created. Since the soft launch in July, the Advocacy toolkit has consistently been one of the Top 5 pages viewed on the nurturing care website. The most popular sections in the toolkit are the key messages, country profiles, and the page defining nurturing care and the five components. To enable further dissemination of the toolkit, additional activities are planned in Q4 2020 and Q1 2021 including i) an animated explainer video to help users understand what is in the toolkit, ii) coordinated promotion of the toolkit on partners’ social media channels, iii) promotion of the toolkit on PMNCH’s digital living platform, iv) launching the toolkit alongside a launch of PMNCH’s COVID-19 toolkits, and v) a webinar in 2021. |  |  | Successfully completed and widely disseminated |
| Develop & disseminate quarterly e-newsletters capturing updates regarding NCF implementation & disseminating new resources |  |  | Two eblasts sent out in July and October. The March eblast was developed but was decided not to send it as it fell right at the start of the pandemic. It was decided to delay the December newsletter until Quarter 1 2021 so as to include the Humanitarian settings brief and the global consultation on the Nurturing care handbook. |
| Identified and negotiated two LOAs with two regionally focused NGOs from Latin America and Africa, respectively, to generate political support for WCAH at the highest level, including support for ECD. |  |  | Completed |
| ACCOUNTABILITY Partners: Use country profiles, scorecards and equity analysis for review and remedial action in 5-10 countries. Secretariat: Synthesize progress; support dev.& dissem. of country profiles & analysis, & tools/mechanisms to strengthen accountability |  |  |  |
| Launch updated ECD country profiles at the Accountability Breakfast during UNGA and on the NCF website. |  |  | Launch of the 2020 ECD Country profiles at the Accountability Breakfast and disseminated via the event website |

| Adolescents Health and Well-Being – 2020 Priority Deliverables | Status |  | Additional details/comments |
| --- | --- | --- | --- |
|  | 6m | 1y |  |
| ANALYSIS Partners: Develop innovation and knowledge briefs; publish and widely disseminate multisectoral case studies Secretariat: Facilitate consensus building and make available agreed knowledge and innovation products |  |  |  |
| Digital resources on adolescent well-being Adolescent health and wellbeing resource hub on PMNCH-website developed for youth-led and youth-serving organisations, incl. COVID19 impact on AY. |  |  | The resource hub is live along with the new PMNCH website, which includes products – news, op-eds, infographics, feature stories, events, fact sheets, Q&As, guidelines and databases. The hub also includes a section for blogs and op-eds written by AYC members. |
| Conceptual framework on adolescent well-being a) Acting on the recommendations of Call to Action for Adolescent, develop a definition of and a conceptual Framework for Adolescent Wellbeing. b) Develop 15 background papers on adolescent well-being based on the framework. c) Publish a political comment endorsed by heads of H6+ agencies, governments, and AYC leaders. d) Develop a BMJ series on Adolescent Wellbeing e) Hold regional multi-stakeholder consultations in July/August 2021 |  |  | a) Definition and a conceptual framework for adolescent wellbeing agreed upon all stakeholder. The commentary on the definition and framework has been published in JAH and can be found here. The commentary has been promoted widely with a social media toolkit. b) Partners have developed 15 background papers on Adolescent well-being. Paper: 1 and 15 have been translated in full into French, Spanish, and Arabic and the abstracts of papers 2-14 have been translated. This was completed on April 19th, 2021. The papers are going to be uploaded on the website and will be disseminated. c)The political comment has been published in the BMJ on March 31st, 2021, and promoted widely with a social media toolkit and partner support d) On track: Currently in conversation with the BMJ to develop a BMJ series on Adolescent Wellbeing which will include analysis articles on programming as well as opinion pieces and commentaries on adolescent wellbeing. e) On track: Planning for 7 regional multi-stakeholder consultations led by WHO regional offices. |
| Adolescent Well-being products during Covid-19 Knowledge summary (KS) and advocacy briefs on adolescent well-being issues have/are being developed and will be disseminated widely: 1) Adolescent mental health video launched in Sept. 2020 and promoted widely; 2) Adolescent empowerment and engagement developed. Dissemination to start in May 2020, 3) Climate change and health with a focus on adolescents and youth advocacy brief – to be completed by Sept./Oct.2020, 4) COVID-19 AY products including infographics and social media packages released on a rolling basis, May 2020 onwards. |  |  | 1) Product 1 is completed and disseminated. The video can be found here. The video on adolescent mental health and COVID-19 was launched during the CORE Group conference 27-28 January 2021. 2) Product 2 is completed and can be found here. 3) Product 3 is completed and will be launched at the Pre-COP. 4) Product 4 is completed – the infographics can be found here. All knowledge summaries can be found here. COVID-19 AY products have been developed including: -Op-ed published in the Telegraph (titled Young people want to contribute to tackling COVID-19) for International Youth Day in August 2020 and In this time of COVID-19 a new consensus on how we should be working to improve adolescent well-being is long overdue on the PMNCH website. |
| ALIGNMENT Partners: Align partners to develop 5-10 national AHWB Plans, and ensure meaningful engagement of adolescents and youth (AY) in national health planning processes, incl. GFF ICs Secretariat: Provide capacity-building support to 5 youth-led coalitions to engage meaningfully in national planning processes; support national multi-stakeholder platforms to prioritize investments in AY health & well-being; |  |  |  |
| Meaningful Adolescent and Youth Engagement Improving meaningful AY engagement in decision-making at global levels: Expand AY rep. in national, regional and global planning and dialog (incl. but not limited to, EWEC HLSG; WHA; UNGA; IPU Assembly; GFF Investment Group, IPU Assembly, UN Youth Strategy, AU, PMNCH Board, etc.). |  |  | Ongoing and on track. - AY is represented across various WGs and thematic groups, PMNCH Board and EC. As part of the governance restructure every working group has a representative under 30. - Adolescents and youth represent are engaged in global events incl. the Core group conference, ECOSOC youth forum side event, Lives in the Balance Summits (1-3), Global Youth Meet, with plans confirmed for AY engagement in the upcoming High Level Political Forum (opening plenary and panels), Generation Equality Forum and Accountability Breakfast on the side-lines of the UN General Assembly. - Young people have also been engaged in writing and peer reviewing the 15 background papers on adolescent well-being - Remuneration is provided to ~40 young people for their time and expertise, as part of the grantee agreement with Youth Lead. - The new brochure (updated based on the version developed in December 2018) documenting the work of the AYC and opportunities for engagement (currently underway). Statement from EXD on International Youth Day, 12 August 2020 - Driving meaningful adolescent and youth engagement in PMNCH and beyond ED PMNCH invited to address the global IFMSA cohort, as part of the Youth Pre World Health Assembly in 2021. ED intervention on ‘Young Voices in Global Health’ was very well received. Social Media impact here and here. |
| Advocating for change for adolescents Roll-out of the 'Advocating for change for adolescents' toolkit to 11 countries: More than 10,000 youth from over 500 networks at national and subnational level are engaged in national policy dialogues, planning processes on WCAH. Advocacy priorities incl. Comprehensive Sexuality Education in Cameroon, Youth Friendly Services Provision in Malawi, ASRH Policy implementation in Kenya, implementation of the RKSK (adolescent health program) in India and facilitating meaningful AY engagement and increased funding for Adolescents in the Basic Health Care Provision Fund in Nigeria. Additional six countries for scale-up incl. Ghana, Liberia, Mexico, Sierra Leone, Zambia and Zimbabwe. |  |  | APW for Plan Canada in place with end date 31 May 2021. Deliverables for review received. Grantee orgs selected. RFP for selection of grant manager published and bids received (on hold). Selected grantee organizations kept in loop and updated as regards to the project through regular communication by AYC chair and Secretariat. Expected roll-out date is (TBC) 2021. |
| Collaboration with GFF on AY Engagement. PMNCH facilitated AYC representation on the GFF Investors’ Group, serving a two-year term, appointed in mid-April 2020 and an AY addendum to the GFF CSO Strategy. |  |  | Completed |
| Engagement with EWEC LAC Collaboration with EWEC LAC continues to mainstream meaningful and sustainable partnership with young people in LAC. 1)In Honduras, efforts have resulted in an intersectoral and multidisciplinary review of the Nat. Adolescent Pregnancy Prevention Program using an equity, human rights based and gender sensitive approach. In addition, Honduras has dev. a multi-sectoral adolescent health strategy. Based on experience in Chile, Honduras and Dominican Republic, a scientific article is being developed to document innovative use of data to plan and design programmes for vulnerable adolescents. Peru, Chile and Columbia are documenting mechanisms for meaningful youth engagement. 2) Disseminated widely Country AY Country Profiles developed by WHO through webinars & social media infographics. 3) In collaboration with EWEC LAC facilitate the completion of WCAH country profiles for 7 LAC countries, of which URU, ARG and PER, are in the process of developing national Equity Profiles. A regional Health Equity report is being developed in collaboration with Pelotas University and will include health equity profiles of 12 countries. |  |  | - Two studies were completed and published on Guatemala on ECD and accountability for WCAH. - A knowledge-brief documenting national and local mechanisms in three countries for meaningful AY engagement was developed. The protocol went through ethical review and is currently ready to be implemented in Chile, Argentina, Peru and the Dominican Republic. - PAHO collaborated with Pro Familia Colombia, IFFP COL and UNICEF to document the lived experiences of women, adolescents and youth during the COVID-19 crisis. - EWEC LAC collaborated with PMNCH to translate a COVID-19 video series to Spanish and Portuguese and disseminate across the Latin America region. - EWEC-LAC disseminated the Spanish version of the ‘Advocating for change for adolescents’ toolkit with partners in the region, particularly in Mexico. - 22 interactive country profiles were developed with technical support from the Federal University of Pelotas on inequalities in women’s, children’s, and adolescents’ health, using data from household surveys available for these countries |
| ADVOCACY Partners: Deliver multisectoral country-specific campaigns for improved AYHW in 5-10 countries Secretariat: Support organisation of 5 campaigns; support national and global champions and 10 youth coalitions to advocate (using the Advocacy Toolkit) |  |  |  |
| Call to Action for Adolescent well-being Mobilizing more than 300 endorsements for a Call to Action. PMNCH will organize a round of digital global and regional consultations with partners. |  |  | Ongoing. 2 MS briefings organised in Feb and July 2020. MS outreach group set up to mobilise endorsements. Mobilisation process a little delayed because of Covid-19 mobilise support: 1) a panel on call to action for adolescent was organised at the ECOSOC youth forum on 7th of April. The panel was co-hosted by Govt of Philippines Costa Rica. 700 youth from 5 regions AFRO, EMRO, SEARO, EURO and the Pacific registered to participate in the discussions with government reps Link to report here and here. 2) An intervention on the Call to Action made by the HCPA at the CSW. The intervention can be found here. |
| ACCOUNTABILITY Partners: Track and report on progress, including country profiles and score-cards, as well as equity analysis for review and remedial action in 5-10 countries Secretariat: Track AY commitments; synthesize progress on outcomes; support 5 youth-led coalitions to conduct accountability/advocacy (incl. dissem. of country profiles and equity analyses) |  |  |  |
| Global Meaningful Adolescent and Youth Engagement Consensus Statement (MAYE) Global Meaningful Adolescent and Youth Engagement Consensus Statement: mobilize at least an additional 50 endorsements with FP2020/IYAFP and implement the accountability system to track actions in 2020-2021. |  |  | Over 200 endorsements have been secured for the Global Consensus Statement. Grant with IYAFP on the accountability system is ongoing. Survey to endorsing organizations was finalized, with over 100 partners in response. A consultant was recruited to develop the annual accountability report. Report is under review, pending sign off and FENSA clearances. Publication on partners’ website expected by end of May 2021. Request for proposals for Practical Guidance to Operationalize Global Consensus Statement on MAYE – selection process is underway to be finalized in June 2021. TORs for Steering Committee of youth-led and youth-serving partners to guidance and support the work drafted. Concept note for the guidance on improving MAYE in institutions. Concept note available here: |

| QED in Services – 2020 Priority Deliverables | Status |  | Additional details/comments |
| --- | --- | --- | --- |
|  | 6m | 1y |  |
| ANALYSIS Partners: Develop QED innovation and knowledge briefs, publish and disseminate multisectoral case studies in BMJ Secretariat: Facilitate consensus building & make available agreed knowledge and innovation products through various means |  |  |  |
| BMJ series – articles on RMNCH coverage: 1) Closing the inequality gaps in reproductive, maternal, newborn and child health coverage: slow and fast progressors: https://gh.bmj.com/content/5/1/e002230 shows that progress in coverage in RMNCH remains insufficient at the national level and across equity dimensions to accelerate towards UHC by 2030, and 2) Large and persistent subnational inequalities in RMNCH intervention coverage in SSA https://gh.bmj.com/content/5/1/e002232 |  |  |  |
| ALIGNMENT Partners: Align partners behind QoC Framework to strengthen QED policies and programmes in 5-10 countries Secretariat: Support MSP, ensuring more meaningful engagement to integrate QED into national plans & strategies in 5+ QoC network countries |  |  |  |
| Incorporate QED principles and guidance into proposals for supporting national multi-stakeholder platforms through the H6 in 10 countries (India and Burundi available here: https://drive.google.com/open?id=1u8Z5Lv6LVls-KL3VweYBfYOCTDo-LNb5 ). See cross cutting. |  |  | Ongoing - 7 countries have prioritised QED in their MSP plans. H6 report on the progress of work has been received |
| ADVOCACY Partners: Conduct advocacy in 5-10 countries & promote QED globally in UHC delivery, incl. through roll out of “What We Want” campaign Secretariat: Facilitate development of QED advocacy toolkit and its dissemination and broad use by partners; support and co-organize advocacy campaigns |  |  |  |
| Advocate for QED through small grants as well as PMNCH's COVID-19 response, see cross cutting |  |  |  |
| ACCOUNTABILITY Partners: Track QED commitments and outcomes via accountability mechanisms including social accountability; strengthen citizen hearings Secretariat: Synthesize progress; support dissemination of country profiles and equity analysis; use tools and mechanisms to strengthen accountability, incl. social accountability mechanisms |  |  |  |
| Track EWEC, QED specific commitments and include analysis in the Global Strategy Progress Report being launched at UNGA 2020, see cross cutting. The QED-focused EWEC Commitments have been tracked and the progress analysed; this analysis contributed to the 2020 GSPR Report released on 25 September and available at the following link: https://protect.everywomaneverychild.org/ |  |  |  |

| Sexual and Reproductive Health and Rights – priority deliverables 2020 |  | Status |  |  |  | Additional details/comments |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 6m |  | 1y |  |  |
| ANALYSIS Partners: Disseminate and use SRHR in UHC knowledge brief and multisectoral knowledge products to influence policy and planning Secretariat: Facilitate consensus building; make available agreed knowledge and innovation products, including ODA future trends for SRHR to influence policy |  |  |  |  |  |  |
| Collaboration with journal Sexual and Reproductive Health Matters in developing a special issue on SRHR in UHC, including 30 peer-reviewed papers, 15 of which are in the final phases of second round review and copy editing. There was a strong response from countries (15 LMICs), as well as some regional papers. The first set of papers will be launched electronically in June 2020, with a webinar anchored by PMNCH Board Chair, Helen Clark, and supported by social media. Additional papers will be released in the Fall to coincide with the Dubai Global Symposium on Health Systems Research, and finally the case studies will be launched in December to coincide with UHC Day. |  |  |  |  | To date, papers in the series have had over 15,000 individual views. The final 6 papers in the series were released in December 2020, with one last commentary pending to be published in January 2021, and key messages were shared at the Lives in the Balance 2 Summit around UHC Day. Additional activities are being planned for SRHR advocacy in Q2 2021. |  |
| Commentary for H. Clark looking at 'building back better' after Covid-19 to better integrate SRHR in UHC benefit packages, to be submitted to the SRHM journal |  |  |  |  | Commentary published and widely promoted through social media. Currently, it’s the second most viewed paper in the series, with nearly 2,000 downloads from the SRHM website. |  |
| ALIGNMENT Partners: Adopt integrated definition and essential SRHR interventions in UHC in 5-10 national plans (including GFF ICs) Secretariat: Promote inclusion of SRHR in 5 national UHC and GFF ICs through support to CSO coalition building and meaningful engagement |  |  |  |  |  |  |
| SRHR network meeting held in January 2020, with over 35 organizations and over 50 participants joining in. Work is currently underway to develop an online community of practice hub, which compiles resources and allows for greater collaboration between partners. Calls are expected to be convened quarterly. |  |  |  |  | Plans being revisited to align with new PMNCH strategy. |  |
| ADVOCACY Partners: Advocate for adoption of comprehensive, integrated definition of SRHR, and incl. of SRHR in UHC through publications, websites, events, campaigns and media Secretariat: Produce advocacy materials on positioning SRHR within WCAH life course approach, UHC and the SDGs; amplify through website, events, joint campaigns, etc. |  |  |  |  |  |  |
| Development of advocacy materials related to the impacts of the COVID-19 pandemic on the provision of SRHR services. This may include digital assets for social media; messaging to include in the PMNCH WhatsApp; toolkits; webinars; opinion editorials; etc. |  |  |  |  | Social media tools developed and widely promoted. COVID-19 live digital compendium includes section on SRHR. Numerous opinion editorials supported for Helen Clark including on violence against women published in the Telegraph; editorial on impact of COVID-19 on women and children (including SRHR language) in Thomson Reuters; and a blog in the BMJ on a ‘new deal’ for women, children and adolescents in the wake of COVID-19. SRHR was also included as a crucial component of the digital toolkits for WCAH and COVID-19, launched in December 2020. |  |
| PMNCH to coordinate planning of webinar launch of the SRHM journal themed issue on SRHR and UHC, focusing on the rights perspective. Webinar target of 500 participants, and will highlight key findings from the issue, with the lens of Covid-19 and its impact on SRHR in UHC. To include participation of Helen Clark. |  |  |  |  | Webinar held on June 15, moderated by Gita Sen and with Helen Clark delivering keynote remarks. Attended by over 900 participants. |  |
| ACCOUNTABILITY Partners: Track progress (including country profiles and equity analysis); improve and align ODA reporting Secretariat: Track commitments and synthesize progress on outcomes (incl. country profiles & equity analysis) and align reporting |  |  |  |  |  |  |
| Contributions to EWEC Global Strategy commitments report, including tracking commitments for and progress of SRHR. SRHR-focused EWEC Commitments tracked and progress analysed; this analysis contributed to the 2020 GSPR Report released on 25 September. They are available at the following link: https://protect.everywomaneverychild.org/ |  |  |  |  | Completed |  |

| Empowerment of Women, Girls and Communities – priority deliverables 2020 | Status |  | Additional details/comments |
| --- | --- | --- | --- |
|  | 6m | 1yr |  |
| ANALYSIS Partners: Develop and update evidence on WCA as agents for change; remove barriers to realizing potential (including community engagement strategies for improving WCAH) Secretariat: Knowledge products made available, incl. innovative approaches & synthesis of economic analysis in support of social, behavioural & community engagement (SBCE) |  |  |  |
| BMJ papers on empowerment launched during PMAC 2020 in Bangkok: https://www.bmj.com/leaving-no-one-behind & https://www.who.int/pmnch/media/news/2019/health_for_all_by_2030/en/ |  |  |  |
| PMNCH is partnering with WHO, Open Consultants, Duke University, to review costing and economic analysis of Social Behavioural Community Engagement (SBCE) strategies that empowers communities for RMNCH. The work is led by WHO. |  |  | This work is ongoing and PMNCH is working closely with partners and WHO MCA on this |
| ALIGNMENT Partners: Effective interventions (incl. SBCE economic analysis) increasingly included in national plans, as well as laws, policies and social norms that remove barriers Secretariat: Facilitate consensus-building; synthesize economic analysis to influence policy; produce tools and materials on WCAH for parliamentarians |  |  |  |
| Women’s empowerment is a key theme addressed in the PMNCH Covid-19 toolkit / compendium, for instance through short animated videos for public-facing information on health and self-care during Covid-19, translating the latest WHO advice, e.g. breastfeeding and adolescent mental health. |  |  | Women’s empowerment is included as components of the toolkits and the compendium and elements of this has been included in the health and self-care videos; e.g. breastfeeding during COVID-19 video |
| ADVOCACY Partners: Advocate for enhanced self-care and care-seeking behaviour, as well as empowerment issues Secretariat: Produce advocacy materials; develop advocacy roadmap with Champions; co-organize campaigns and events |  |  |  |
| See cross cutting |  |  |  |
| ACCOUNTABILITY Partners: Track progress (incl. country profiles) & use data for review & remedial action in 5-10 countries; strengthen political and social accountability mechanisms Secretariat: Support development of accountability tools and materials; support civil society coalitions to conduct social accountability |  |  |  |
| See cross cutting. |  |  |  |

| Humanitarian and Fragile Settings – priority deliverables 2020 | Status |  | Additional details/comments |
| --- | --- | --- | --- |
|  | 6m | 1y |  |
| ANALYSIS Partners: Disseminate knowledge briefs on WCAH in HFS and multisectoral knowledge products; use these to influence policy and planning in 5-10 countries Secretariat: Facilitate consensus on evidence and develop synthesis on innovative solutions for WCAH in HSF; support work in 5+ countries |  |  |  |
| Digital toolkits and other knowledge translation products (e.g. a review of socio-economics impacts and mitigation strategies for WCAH in HFS – see cross cutting for more info) around the impact of COVID-19 on WCAH in HFS to be developed and made available. The first set of toolkits on MNCAH were launched in December 2020 and included HFS sensitive resources. |  |  | On track. The digital toolkit on WCAH in HFS and COVID-19 has been developed and is being finalized for launch in February 2021. |
| Knowledge translation products (advocacy toolkits, policy briefs, webinars) associated with the Lancet Series on RMNCAH+N in Conflict Settings to be developed by the BRANCH Consortium, in collaboration with PMNCH and disseminated by PMNCH following the launch of the Lancet Series on RMNCAH+N in Conflict Settings https://www.branchconsortium.com/resources |  |  | Lancet Series launched in January 2021. The launch event was viewed by 1,343 people from 85 countries representing governments, health practitioners, UN agencies, the private sector, civil society, media, researchers and academia. 5 knowledge translation briefs launched in January 2021: https://www.branchconsortium.com/resources |
| Discussion paper on common understanding of what fragility means in the context of WCAH in HFS and the difference between HFS-settings – dev. by ICMHD, July 2020. |  |  | Completed |
| Situational analysis to be conducted, with WHO and UNICEF as the lead technical partners, on the continuum of care in HFS to synthesis HFS sensitive guidance on WCAH to identify guidance evidence gaps and priority areas for action around WCAH in HFS 0. The situational analysis will further inform the dev. of a Global Roadmap Plan for Accelerating Progress for WCAH in HFS (to complement the HFS Newborn Roadmap) to be launched in May 2022 |  |  | Concept note developed. Consultant hired for situational analysis and protocol of situation analysis developed. |
| Peer reviewed papers to be developed, with UNFPA and ICM as lead partners, on midwives and other frontline health workers in HFS as part of the post S State of World Midwives Report launch plan, as well as PMNCH’s advocacy work related to the importance of midwifery and nursing in providing quality MNCAH care. |  |  | Ad-hoc Advisory group established. Concept note developed. Contract for situational analysis and systematic review issued. Situational analysis underway with quant component complete and qualitative component in process. Protocol for systematic review published, and systematic review underway. Contributions made to the SoWMY report drafts. |
| ALIGNMENT Partners: Forge consensus on integrating WCAH into HFS; encourage multi-stakeholder groups to agree and execute action plan around WCAH in 5-10 conflicted countries Secretariat: Facilitate engagement across constituencies; support consensus-building, dissemination and advocacy; amplify findings and action plans |  |  |  |
| PMNCH HFS Steering Group established to align partners and advocate for a continuum of care approach to WCAH in HFS - Concept Note and TORs: https://drive.google.com/drive/u/0/folders/15lRcVZHPdLVmv-YDEEtNM5jX1UfAm2Mr |  |  |  |
| Virtual Case studies Hub on WCAH in Humanitarian and Fragile Settings to be developed as part of PMNCH’s new Digital Platform to facilitate knowledge exchange and sharing by providing curated and linked resources, from the development and humanitarian sectors, on SRMNCAH in HFS such as case studies, national assessments, good practices (including on the humanitarian-development nexus) and related derivate knowledge translation products in a centralised and living hub |  |  | Concept note developed. Work on Case Study hub to begin once the Digital Platform has gone live in 2021. |
| Facilitate the uptake of evidence and recommendations from the Lancet Series on RMNCAH+N in Conflict Settings by supporting the organization of 5 regional workshops led by the BRANCH Consortium. This activity might be delayed to 2021 due to delays because of COVID-19. |  |  | Letter of Agreement to formalize collaboration with BRANCH signed. Planning for 3 regional workshops underway |
| ADVOCACY Partners: Develop advocacy products for integrating WCAH into HFS and for innovative solutions to accelerate progress Secretariat: Develop advocacy materials and roadmap to amplify findings and action plans of WCAH in HFS |  |  |  |
| Launch of the Lancet Series on RMNCAH+N in Conflict and dissemination of Series findings to be supported with an aim to influence policy and programs around WCAH in HFS. The advocacy activities will include: a) high level launch event; b) digital advocacy campaign; c) BRANCH’s digital platform; d) advocacy toolkits and policy briefs developed by BRANCH for PMNCH to disseminate widely, |  |  | Lancet launch event delayed to Jan 2021 due to delays on Lancet side Available here https://www.branchconsortium.com/ The launch event was viewed by 1,343 people from 85 countries representing governments, health practitioners, UN agencies, the private sector, civil society, media, researchers and academia. 5 knowledge translation briefs launched in January 2021: https://www.branchconsortium.com/resources |
| Conduct advocacy to influence and drive policy change re Continuum of Care approach for WCAH in HFS. This incl.: a) Dev. advocacy & political engagement roadmap for WCAH in HFS that will feed into the overarching PMNCH advocacy strategy, b) Contributing to the advocacy around key issues impacting WCAH in HFS including COVID-19 through toolkits, webinars, social media messaging (infographics, tweets, videos) , c) Integration of essential interventions for WCAH in UHC schemes in HFS d) Dissemination of various PMNCH HFS supported or partner products (Roadmap for Newborns in Emergencies, ECD advocacy toolkit, etc.). |  |  | HFS Advocacy and Political Engagement Roadmap developed and shared with PMNCH AWG co-chairs. Roadmap for newborns in emergencies and EWEC@10 report launched and disseminated through social media channels. |
| ACCOUNTABILITY Partners: Establish monitoring and accountability framework for WCAH in HSF, report progress and strengthen accountability mechanisms Secretariat: Facilitate consensus around monitoring and evaluation framework for WCAH in HFS; disseminate progress reports and strengthen accountability mechanisms (e.g. tools) |  |  |  |
| Peer reviewed research paper on ‘WCA in conflict countries: an assessment of inequalities in intervention coverage and survival’ developed with Countdown to 2030, as part of the Leaving no one behind BMJ Series to track progress towards the Global Strategy, launched at PMAC in Jan 2020. |  |  | Completed |
| Track HFS specific EWEC commitments and incl. commitment analysis in the Global Strategy Progress Report being launched at UNGA 2020, see cross cutting for more information. |  |  | Completed |
| Commentaries for the Lancet Series on RMNCAH+N in Conflict Settings on the link between the findings of the Series and accountability for future action to be developed and launched alongside the Lancet Series launch. |  |  | Commentary from Helen Clark as Chair of PMNCH Board on the Lancet Series ‘’ A commitment to support the world's most vulnerable women, children, and adolescents’’ published in the Lancet. |

Final financial summary for 2020 (01 Jan 2020 to 31 December 2020)

Table 1 below provides information on the total expenditure associated with the delivery of PMNCH’s 2020 workplan to 31 December 2020, together with allocations of revenues and utilization by workstream and set against the Essential Level budget of US$ 10 million.

Table 1: Financial summary for 2020 - available resource, expenditure, and implementation rate (US$), from 01 Jan to 31 December 2020.

| PMNCH 2020 workplan categories | Budget | Resources | Expenditure | Implementation against resources |
| --- | --- | --- | --- | --- |
| Workstream 1. Early Childhood Development | 1,700,000 | 1,274,486 | 1,255,259 |  |
| Workstream 2. Adolescents’ Health and Well-Being | 1,745,000 | 1,672,762 | 1,647,528 |  |
| Workstream 3. Quality, Equity and Dignity in Services | 1,705,000 | 1,115,175 | 1,098,352 |  |
| Workstream 4. Sexual and Reproductive Health and Rights | 1,690,000 | 1,354,141 | 1,333,713 |  |
| Workstream 5. Empowerment of Women, Girls and Communities | 1,540,000 | 1,035,520 | 1,019,898 |  |
| Workstream 6. Humanitarian and Fragile Settings | 1,620,000 | 1,513,452 | 1,490,620 |  |
| Total | 10,000,000 | 7,965,535 | 7,845,370 | 98% |